## HRInputs
Variable | Value
batchSize | 6
stepsPerOrder | 3
weekInterval | 2
maxClientsPerMonth | 6
costPerStep | 2000
handlingCost | 1500
bonusProfit | 15000

## Forecast
Month | Steps Required | Clients Completed | Cumulative Clients | Month | Production Cost (€) | Handling Cost (€) | Bonus (€)
2025-07-01 | 18 | 6 | 6 | 2025-07-01 | 36000 | 9000 | 0
2025-08-01 | 12 | 0 | 6 | 2025-08-01 | 24000 | 0 | 0
2025-09-01 | 12 | 6 | 12 | 2025-09-01 | 24000 | 9000 | 15000
2025-10-01 | 12 | 6 | 18 | 2025-10-01 | 24000 | 9000 | 0

## Calendar
Client | Batch | Step 1 | Step 2 | Step 3
Client 1 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01
Client 2 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01
Client 3 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01
Client 4 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01
Client 5 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01
Client 6 | 1 | 2025-07-01 | 2025-07-01 | 2025-07-01
Client 7 | 2 | 2025-08-01 | 2025-08-01 | 2025-09-01
Client 8 | 2 | 2025-08-01 | 2025-08-01 | 2025-09-01
Client 9 | 2 | 2025-08-01 | 2025-08-01 | 2025-09-01
Client 10 | 2 | 2025-08-01 | 2025-08-01 | 2025-09-01
Client 11 | 2 | 2025-08-01 | 2025-08-01 | 2025-09-01
Client 12 | 2 | 2025-08-01 | 2025-08-01 | 2025-09-01
Client 13 | 3 | 2025-09-01 | 2025-10-01 | 2025-10-01
Client 14 | 3 | 2025-09-01 | 2025-10-01 | 2025-10-01
Client 15 | 3 | 2025-09-01 | 2025-10-01 | 2025-10-01
Client 16 | 3 | 2025-09-01 | 2025-10-01 | 2025-10-01
Client 17 | 3 | 2025-09-01 | 2025-10-01 | 2025-10-01
Client 18 | 3 | 2025-09-01 | 2025-10-01 | 2025-10-01

## HRInstructions
📌 OBJECTIVE:
Build a macro-enabled tool that forecasts when clients will receive their furniture and what production capacity is needed.
📅 SCENARIO DETAILS:
- Orders are delivered in 3 production steps (e.g., cutting, assembly, finishing), 2 weeks apart.
- Orders are grouped into 3 sequential batches of 6 clients each.
- The next batch can only start once the previous batch completes all 3 steps.
- No more than 6 new clients can be onboarded each month.
- The project starts in July 2025.
💸 COSTS:
- Cost per production step: €2,000
- Handling cost per client: €1,500
- Bonus profit: €15,000 when 10 clients have completed all steps
✅ TASKS TO COMPLETE:
1. Create an INPUTS section with variables (batch size, number of steps, intervals, costs).
2. Create a calendar (macro-generated) showing which month each client receives each step.
3. Automate a FORECAST table showing:
- How many production steps are required each month
- Cumulative clients completed
4. Automate a COST ESTIMATION summary including:
- Monthly production costs
- Handling costs
- Bonus calculation (after 10 clients)
5. Create at least one CHART showing forecasted production volume.

## Inputs
Variable | Value
batchSize | 6
stepsPerOrder | 3
weekInterval | 2
maxClientsPerMonth | 6
costPerStep | 2000
handlingCost | 1500
bonusProfit | 15000